## Overall Project Status
Sr No | Task |  | Stage1: Understanding/ development | Stage2: Review | Stage3: Feedback Implementation | Stage4: Final Documentation | Overall Status
[7 empty] | Planned date of competition | Actual date of competition
1 | Spec Understanding & Feature Extraction |  | 2023-09-09 | 2023-09-09 | NA | NA | 2023-09-09 | 2023-09-09
2 | Testplan Development |  | 2023-09-09 | 2023-09-09 | NA | NA | 2023-09-09
3 | Verification Plan Development (TB Architecture, Checker/assertion Planning) |  | 2023-09-09 | 2023-09-09 | NA | NA | 2023-09-09
4 | Development Phase | TOP, Environment, configuration class, Agent | 2023-10-09 | 2023-10-09 | NA | NA | 2023-10-09
|  | Generator, Testcases, Transaction class | 2023-10-09 | 2023-10-09 | NA | NA | 2023-10-09
|  | Driver, Interface | 2023-10-09 | 2023-10-09 | NA | NA | 2023-10-09
|  | Monitor, scoreboard | 2023-10-09 | 2023-10-09 | NA | NA | 2023-10-09
|  | Assertion, checker Plan | 2023-10-09 | 2023-10-09 | NA | NA | 2023-10-09
6 | Run & Validation of Sanity | Sanity test | 2023-11-09 | 2023-11-09 | NA | NA | 2023-11-09
7 | Development & validation of Other/Advance Scenarios | Scenarios | 2023-12-09 | 2023-12-09 | NA | NA | 2023-12-09
8 | Regression Setup | Script Update | 13/09/23 | 13/09/23 | NA | NA | 13/09/23
|  | Run regression | 13/09/23 | 13/09/23 | NA | NA | 13/09/23
9 | Coverage | Functional coverage planning | 14/09/23 | 14/09/23 | NA | NA | 14/09/23
|  | Coverage development | 14/09/23 | 14/09/23 | NA | NA | 14/09/23
|  | Identify missing coverage specific scenarios | 14/09/23 | 14/09/23 | NA | NA | 14/09/23
|  | Development of missing coverage specific scenarios | 14/09/23 | 14/09/23 | NA | NA | 14/09/23
|  | Coverage closure | 14/09/23 | 14/09/23 | NA | NA | 14/09/23
10 | Assertion | Development | 15/09/23 | 15/09/23 | NA | NA | 15/09/23
|  | Validation & Closure | 15/09/23 | 15/09/23 | NA | NA | 15/09/23

## Daily Status
Date | Date of Entry | Work Status of the Entry | Task Detail | Action Item
| 2023-08-09 | Started of the TDP RAM Project | 1. Created basic Architecture for UVC 2. Created github repository for the project and learned basic commands of git like how to work on local machine and update them on git | None

## Notes
Can use different color coding for highlight
If task is completed: | Done
If task is in progress: | In-Progress
If task is on hold: | On-Hold
If task is delayed or we are running behind the schedule:
If need any help
Status Owner Day wise | Owner
Monday
Tuesday
Wednesday
Thursday
Friday